## DMAIC_Roadmap
Lean Six Sigma DMAIC Roadmap
| Purpose | Key Tools |  |  |  | Key Outputs
Define | To establish a quantified problem statement, objective and business case that will become the foundation to your Six Sigma project. Conduct stakeholder analysis, select team members and kick-off your project. | Primary Metric | Process Map | Project Charter | Project Plan | * Process Map * Gather VOC * Translate VOC to CTQ's * QFD/HOQ * COPQ * Primary & Secondary Metrics * Establish Project Charter * Stakeholder Analysis * Team Selection * Project Plan
Measure | Refine your understanding of the process. Assess process capability relative to customer specifications. Validate measurement systems. Brainstorm potential x's. | C&E | SIPOC | FMEA | Cpk | * Early Y=f(x) Hypothesis * Detailed Process Map * SIPOC * Cause & Effect Diagram * Cause & Effect Matrix * FMEA * Basic Statistics * Normality Test * Capability Analysis * Gage R&R
Analyze | Conduct data collection and planned studies in order to eliminate non-critical x's and validate critical x's. Establish a stronger and quantified Y=f(x) equation. | Normality Test | ANOVA | 2 Sample t-test | Equal Variances | * Narrowed Y=f(x) * 1 & 2 Sample t-tests * 1 & 2 Proportions tests * Equal variance tests * Normality tests * ANOVA * Moods Median * Mann Whitney * Paired t-test * Chi-Squared test
Improve | Design, test and implement your new process or product under live operating conditions. Pilot solutions if feasible before broadly deploying expensive improvements or products. | Pugh Matrix | Linear Regression | Binary Logistic Regression | DOE | * Refined Y=f(x) * Pugh Matrix * Correlation * Simple Linear Regression * Multiple Linear Regression * Binary Logistic Regression * Full Factorial DOE * Fractional Factorial DOE
Control | Plan, communicate, train and implement your product or process solutions. Ensure control mechanisms are established. Use Poke Yoke, visual controls, SOP's and SPC wherever possible. | Control Plan | SOP's | Communication Plan | SPC | * Control Plan * Training Plan * Refined FMEA * Communication Plan * Standard Operating Procedures * Five-S Audit * Poke Yoke * Visual Controls * Statistical Process Control

## DMAIC_Project_Checklist
D.M.A.I.C Project Checklist
| DEFINE |  | IMPROVE
| 2 | Projecct Charter | 2 | Potential Solutions Developed
| 2 | Business Case (why is this project important) | 2 | Potential Solutions Prioritized
| 3 | Problem Statement & Objective | 2 | Solution Selected
| 2 | Baseline Data (Primary Metric "Y") | 2 | Improvement Pilot/Test Plan
| 2 | Target | 2 | Improvement Pilot/Test Execution
| 2 | COPQ Estimate | 2 | Improvement Verified
| 2 | Project Team | 2 | New Process Capability
| 2 | Project Scope | 2 | Updated Process Map
| 2 | Project Timeline | 2 | Solution Implementation Plan
| 2 | Project Constraints/Dependencies | 2 | Primary Metric Updated
| 2 | High Level Process Map | 2 | COPQ Revision
| 2 | Customer Requirements Identified | 2 | Improve Phase Report
| 2 | Define Phase Report
| MEASURE |  | CONTROL
| 2 | Detailed Process Map | 2 | Full Solution Implementation
| 2 | SIPOC | 2 | Standard Operating Procedures Developed
| 3 | Data Collection Plan (Potential X's) | 2 | Communication Plan
| 2 | Measurement Systems Analysis (Primary Y) | 2 | Training Plan
| 2 | Process Capability Analysis | 2 | Audit Plan
| 2 | List of Possible X's | 2 | Control Charts
| 2 | Prioritized List of X's to be Analyzed | 2 | Control Plan
| 2 | Primary Metric Updated | 2 | Primary Metric Updated
| 2 | COPQ Revision | 2 | COPQ Revision
| 2 | Measure Phase Report | 2 | Full Project Report
ANALYZE
| 2 | Sources of Variation Identified
| 2 | Potential X's Eliminated
| 2 | Root Causes Confirmed (Critical X's Identified)
| 2 | Primary Metric Updated
| 2 | COPQ Revision
| 2 | Analyze Phase Report

## Project_Prioritization
Project Prioritization Matrix
Date: | 2014-10-13
Activity: | Project Prioritization
Facilitator: | John Doe
Business Priorities | ROI | Duration | Cost | Resoruce | Difficulty | Complexity
Weighting (1-10): | 8 | 5 | 6 | 6 | 4 | 4
Projects | [6 empty] | Score
Project #6 | 9 | 9 | 7 | 9 | 9 | 7 | 277
Project #7 | 9 | 9 | 7 | 9 | 9 | 7 | 277
Project #3 | 7 | 9 | 5 | 9 | 11 | 7 | 257
Project #5 | 7 | 9 | 5 | 9 | 11 | 7 | 257
Project #11 | 7 | 9 | 5 | 9 | 11 | 7 | 257
Project #2 | 5 | 7 | 3 | 7 | 9 | 5 | 191
Project #8 | 5 | 7 | 3 | 7 | 9 | 5 | 191
Project #12 | 5 | 7 | 3 | 7 | 9 | 5 | 191
Project #1 | 3 | 5 | 1 | 5 | 7 | 3 | 125
Project #4 | 3 | 5 | 1 | 5 | 7 | 3 | 125
Project #9 | 3 | 5 | 1 | 5 | 7 | 3 | 125
Project #10 | 3 | 5 | 1 | 5 | 7 | 3 | 125

## Project_Charter
Project Title:
|  |  |  | Black Belt | Project Champion | Executive Sponsor |  | MBB/Mentor
Primary Metric |  |  |  |  | Secondary Metric
Problem Statement |  |  |  |  | Business Case
High Level Project Timeline |  |  | Constraints & Dependencies |  | Project Risks |  | Other Diagnostics
Phase | Start | Finish
Define
Measure
Analyze
Improve
Control
Approval/Steering Committee |  |  |  | Stakeholders & Advisors |  | Project Team & SME's
Name |  | Organization |  | Name | Organization | Name |  | Organization

## Scorecard
Basic Scorecard
Calculate
Status |  |  | Q1'15 |  |  | Q2'15 |  |  | Q3'15 |  |  | Q4'15 |  |  | Full Year 2015
Current | FYF | Key Business Metrics | Goal | Fcst | Actual | Goal | Fcst | Actual | Goal | Fcst | Actual | Goal | Fcst | Actual | Goal | Fcst | Actual
1.16 | 0.97 | Operating Expense Reduction | 15 | 12 | 8 | 25 | 25 | 29 | 35 | 36 |  | 25 | 24 |  | 100 | 97
0.96721 | #DIV/0! | Customer Satisfaction | 61 | 58 | 57 | 61 | 58 | 59 | 61 | 59 | 59 | 61 | 61
#DIV/0! | #DIV/0! | Net Income
0 | 1.05 | OWT |  |  |  | 10 | 10 | 0 | 10 | 10 | 13.1 | 40 | 40 |  | 60 | 63
Operating Metrics
3 | 3 | Recall Open Cases
3 | 3 | Recall Open Case Dollars
3 | 3 | Recall Cases w/Purchasing
3 | 3 | Recall Case Dollars w/Purchasing
3 | 3 | Legacy Open Cases
3 | 3 | Legacy Open Case Dollars
3 | 3 | Legacy Cases w/Purchasing
3 | 3 | Legacy Case Dollars w/Purchasing
1 | 1 | OWT Cumulative Parts Reviewed | [6 empty] | 31200 | 3801.6 |  | 52800 | 4966.8 |  | 52800 | 4966.8
1 | 1 | OWT Cumulative Recovery Groups w/TF | [6 empty] | 1213 | 188.7 |  | 1933 | 194.7 |  | 1933 | 194.7
Status Rules: Current status based on forecst vs. goal for future periods and based on actual vs. goal for past period. FYF status based on full year forecast vs.goal untill the year completes.
Status Conditions: Green >=100% of Goal, Yellow 95%-99% of Goal, Red <95% of Goal
$dollars represented in Millions

## FMEA
Failure Modes & Effects Analysis - FMEA
Product or Process Step | Potential Failure Mode | Potential Failure Effects | S | Potential Causes | O | Current Controls | D | RPN | Recommended Actions | Responsible | Actions Taken | S | O | D | RPN
[8 empty] | 0 | [6 empty] | 0
[8 empty] | 0 | [6 empty] | 0
[8 empty] | 0 | [6 empty] | 0
[8 empty] | 0 | [6 empty] | 0
[8 empty] | 0 | [6 empty] | 0
[8 empty] | 0 | [6 empty] | 0
[8 empty] | 0 | [6 empty] | 0
[8 empty] | 0 | [6 empty] | 0
[8 empty] | 0 | [6 empty] | 0
[8 empty] | 0 | [6 empty] | 0
[8 empty] | 0 | [6 empty] | 0
[8 empty] | 0 | [6 empty] | 0
[8 empty] | 0 | [6 empty] | 0
[8 empty] | 0 | [6 empty] | 0
[8 empty] | 0 | [6 empty] | 0
[8 empty] | 0 | [6 empty] | 0
[8 empty] | 0 | [6 empty] | 0
[8 empty] | 0 | [6 empty] | 0
[8 empty] | 0 | [6 empty] | 0
Note on B2: Six Sigma Digest Hint: Use this column to list each Product or Process Step that will be considered in this analysis. Be sure to leave a few empty rows after each entry
Note on C2: Six Sigma Digest Hint: What are all the possible failures of each product or process step being considered? It is likely that you will have more than one failure for each product or process step.
Note on D2: Six Sigma Digest Hint: What are the likely affects of each failure? You may have more than one effect for each failure
Note on E2: Severity
Note on F2: Six Sigma Digest Hint: What are the potential causes of the failure?
Note on G2: Occurrence
Note on H2: Six Sigma Digest: What controls are in place to mitigate or prevent the failures form occurring?
Note on I2: Detection
Note on K2: Six Sigma Digest: What actions are recommend to address the potential failures?
Note on L2: Six Sigma Digest: Who is responsible for the actions?
Note on M2: Six Sigma Digest: Enter the actions taken and then re-asses Severity, Occurance and Detection to ge a revised RPN. This is to be sure your team believes that the potential failures of the product or process have been adequately addressed.
Note on N2: Severity
Note on O2: Occurrence
Note on P2: Detection

## FMEA Ratings
Rating | Severity | Occurrence | Detection
9 | alarming concern | frequent | undetectable
7 | significant concern | routine | somewhat detectable
5 | concerning | occasional | highly detectable
3 | not concerning | not often | certain detection

## Gantt_Chart_Weekly
Gantt Chart Template (Week Format)
Countermeasure | $ Cost | Owner | Start Week | End Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
First Task or Activity |  |  | 2 | 12 | bar: Gantt Chart Template (Week Format) 2 to Gantt Chart Template (Week Format) 12
Second Task or Activity |  |  | 4 | 11 | bar: Gantt Chart Template (Week Format) 4 to Gantt Chart Template (Week Format) 11
Third Task or Activity |  |  | 4 | 18 | bar: Gantt Chart Template (Week Format) 4 to Gantt Chart Template (Week Format) 18
Fourth |  |  | 2 | 26 | bar: Gantt Chart Template (Week Format) 2 to Gantt Chart Template (Week Format) 26
Fifth dependent on completion of fourth
Six task of activity |  |  | 10 | 22 | bar: Gantt Chart Template (Week Format) 10 to Gantt Chart Template (Week Format) 22
Seventh Taks dependent on completion of fifth |  |  | 19 | 47 | bar: Gantt Chart Template (Week Format) 19 to Gantt Chart Template (Week Format) 47

## Gantt_Chart_Monthly
Gantt Chart Template (Month Format) |  |  |  |  | Year 2013 | [11 empty] | Year 2014
Month
Root Cause / Countermeasure / Activity | $ave or Cost | Owner | Start Month | End Month | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
First Task or Activity |  |  | 1 | 8 | bar: Month 1 to Month 8
Second Task or Activity |  |  | 1 | 7 | bar: Month 1 to Month 7
Third Task or Activity |  |  | 1 | 3 | bar: Month 1 to Month 3
Fourth |  |  | 1 | 2 | bar: Month 1 to Month 2
Fifth dependent on completion of fourth |  |  | 3 | 8 | bar: Month 3 to Month 8
Six task of activity |  |  | 4 | 6 | bar: Month 4 to Month 6
Seventh Taks dependent on completion of fifth |  |  | 9 | 14 | bar: Month 9 to Month 14

## SIPOC
S.I.P.O.C. Template
Suppliers | Inputs | Process | Outputs | Customers
Start
Step 1
Step 2
Step 3
Step 4
End

## Control_Plan
Control Plan
| Process: | [6 empty] | Preparer: | [5 empty] | Page: |  | of
| Customer: | [6 empty] | Email: | [5 empty] | Reference No:
| Stakeholder: | [6 empty] | Phone: | [5 empty] | Revision Date:
| Business: | [6 empty] | Owner: | [5 empty] | Approval:
Process |  | Process Step | CTQ/Metric | CTQ / Metric Equation | Specification/ Requirement |  | Measurement Method |  | Sample Size | Measure Frequency | Responsible for Metric | Link or Report Name | Corrective Action |  | Responsible for Action
[5 empty] | LSL | USL

## Communication_Plan
Communication Plan Template
Process/Function Name |  | Project/Program Name |  | Project Lead |  | Project Sponsor/Champion
Communication Purpose:
Target Audience | Key Message | Message Dependencies | Delivery Date | Location | Medium | Follow up Medium | Messenger | Escalation Path | Contact Information

## Training_Plan
Training Plan Template
Project |  | Process |  | Project Lead |  | Business Division |  |  | Sponsor
Who | Where | When | How Many | Key Change/Process | Training Medium | Supporting Docs | Technology Requirements | Other Requirements | Trainer | Status

## Audit_Checklist
Audit Checklist
Target Area: | Statement of Audit Objective: | Auditor: | Audit Date:
Audit Technique | Auditable Item, Observation, Procedure etc. | Individual Auditor Rating (Circle Rating)
Observation | Have all associates been trained? | YES | NO
Observation | Is training documentation available? | YES | NO
Observation | Is training documentation current? | YES | NO
Observation | Are associates wearing proper safety gear? | YES | NO
Observation | Are SOP's available? | YES | NO
Observation | Are SOP's current? | YES | NO
Observation | Is quality being measured | YES | NO
Observation | Is sampling being conducted in random fashion | YES | NO
Observation | Is sampling meeting it's sample size target? | YES | NO
Observation | Are control charts in control | YES | NO
Observation | Are control charts current? | YES | NO
Observation | Is the process capability index >1.0? | YES | NO
Number of Out of Compliance Observations
Total Observations
Audit Yield |  |  | #DIV/0!
Corrective Actions Required
Auditor Comments

## Pugh_Matrix
S | Pugh Matrix Template
+ | Pugh Matrix
- | Owner:
| Measures¦CTQ's¦Factors etc. | Importance Rating | Baseline | Option 1 | Option 2 | Option 3 | Option 4 | Option 5 | Option 6 | Option 7
| Hard Dollar Savings | 7 |  | - | + | - | + | + | + | +
| Operating Expenses | 7 |  | - | S | + | + | + | + | +
| Cost Avoidance | 1 |  | + | + | + | + | + | + | +
| Ongoing Maintenance Expense | 1 |  | + | + | + | S | + | + | -
| ROI (NPV) | 9 |  | + | + | + | + | + | - | +
| Incremental Capital | 5 |  | + | + | - | + | + | + | +
| Operational Stability | 3 |  | + | + | + | + | + | - | +
| Brand/Reputation | 3 |  | + | + | + | + | + | + | +
| Sum of +'s |  |  | 6 | 7 | 6 | 7 | 8 | 6 | 7
| Sum of -'s |  |  | 2 | 0 | 2 | 0 | 0 | 2 | 1
| Sum of Sames |  |  | 0 | 1 | 0 | 1 | 0 | 0 | 0
| Weighted Sum of +'s |  |  | 22 | 29 | 24 | 35 | 36 | 24 | 35
| Weighted Sum of -'s |  |  | 14 | 0 | 12 | 0 | 0 | 12 | 1
| Highest Score Wins |  |  | 8 | 29 | 12 | 35 | 36 | 12 | 34
Baseline = "write your description of the basline here"
Option1 = "description of option 1"
Option2 = "description of option 2"
Option3 = "description of option 3"
Option4 = "description of option 4"
Option5 = "description of option 5"
Key
"+" = Better than baseline
"-" = Worse than baseline
"s" = Same as baseline

## XY_Matrix
Cause & Effect Matrix (XY Matrix)
Date:
Project:
XY Matrix Owner:
Output Measures (Y's)* | Y1 | Y2 | Y3 | Y4 | Y5 | Y6 | Y7 | Y8 | Y9 | Y10
Weighting (1-10):
Input Variables (X's)# | Y1: For each X, score its impact on each Y listed above (use a 0,3,5,7 scale) | Score
X1 | [10 empty] | 0
X2 | [10 empty] | 0
X3 | [10 empty] | 0
X4 | [10 empty] | 0
X5 | [10 empty] | 0
X6 | [10 empty] | 0
X7 | [10 empty] | 0
X8 | [10 empty] | 0
X9 | [10 empty] | 0
X10 | [10 empty] | 0
X11 | [10 empty] | 0
X12 | [10 empty] | 0
X13 | [10 empty] | 0
X14 | [10 empty] | 0
X15 | [10 empty] | 0
X16 | [10 empty] | 0
X17 | [10 empty] | 0
X18 | [10 empty] | 0
X19 | [10 empty] | 0
X20 | [10 empty] | 0
X21 | [10 empty] | 0
X22 | [10 empty] | 0
X23 | [10 empty] | 0
X24 | [10 empty] | 0
X25 | [10 empty] | 0
X26 | [10 empty] | 0
X27 | [10 empty] | 0
X28 | [10 empty] | 0
X29 | [10 empty] | 0
X30 | [10 empty] | 0
XY Matrix Premise: The XY Matrix or "Cause & Effect Matrix functions on the premise of the Y=f(x) equation.
*Rate each "Y" on a scale of 1 to 10 with 1 being the least important output measure
#For each X rate its impact on each Y using a 0,3,5,7 scale (0=No impact, 3=Weak impact, 5=Moderate impact, 7=Strong impact).

## Risk_Mgt_Plan
Risk Management Plan
Company |  | Project/Program Name | Project Lead |  | Project Sponsor/Champion |  |  | Last Updated
Risk ID | Risk Category | Risk Description |  | Risk Impact |  | ImpactRating | Mitigation Action | Responsible | Status

## DPMO_Sigma_Level
| Without 1.5 sigma shift |  |  | With 1.5 sigma shift
Sigma Level | DPMO | Yield | Defect Rate | DPMO | Yield | Defect Rate
1 | 317310 | 68.27% | 31.73% | 697612 | 30.24% | 69.76%
1.1 | 271332 | 72.87% | 27.13% | 660082 | 33.99% | 66.01%
1.2 | 230139 | 76.99% | 23.01% | 621378 | 37.86% | 62.14%
1.3 | 193601 | 80.64% | 19.36% | 581814 | 41.82% | 58.18%
1.4 | 161513 | 83.85% | 16.15% | 541693 | 45.83% | 54.17%
1.5 | 133614 | 86.64% | 13.36% | 501349 | 49.87% | 50.13%
1.6 | 109598 | 89.04% | 10.96% | 461139 | 53.89% | 46.11%
1.7 | 89130 | 91.09% | 8.913% | 421427 | 57.86% | 42.14%
1.8 | 71860 | 92.81% | 7.186% | 382572 | 61.74% | 38.26%
1.9 | 57432 | 94.26% | 5.743% | 344915 | 65.51% | 34.49%
2 | 45500 | 95.45% | 4.55% | 308770 | 69.12% | 30.88%
2.1 | 35728 | 96.43% | 3.573% | 274412 | 72.56% | 27.44%
2.2 | 27806 | 97.22% | 2.781% | 242071 | 75.79% | 24.21%
2.3 | 21448 | 97.86% | 2.145% | 211927 | 78.81% | 21.19%
2.4 | 16395 | 98.36% | 1.639% | 184108 | 81.59% | 18.41%
2.5 | 12419 | 98.76% | 1.242% | 158686 | 84.13% | 15.87%
2.6 | 9322 | 99.07% | 0.9322% | 135686 | 86.43% | 13.57%
2.7 | 6934 | 99.31% | 0.6934% | 115083 | 88.49% | 11.51%
2.8 | 5110 | 99.49% | 0.511% | 96809 | 90.32% | 9.681%
2.9 | 3731 | 99.63% | 0.3731% | 80762 | 91.92% | 8.076%
3 | 2699 | 99.73% | 0.2699% | 66810 | 93.32% | 6.681%
3.1 | 1935 | 99.81% | 0.1935% | 54801 | 94.52% | 5.48%
3.2 | 1374 | 99.86% | 0.1374% | 44566 | 95.54% | 4.457%
3.3 | 966 | 99.9% | 0.0966% | 35931 | 96.41% | 3.593%
3.4 | 673 | 99.93% | 0.0673% | 28716 | 97.13% | 2.872%
3.5 | 465 | 99.95% | 0.0465% | 22750 | 97.72% | 2.275%
3.6 | 318 | 99.97% | 0.0318% | 17864 | 98.21% | 1.786%
3.7 | 215 | 99.98% | 0.0215% | 13903 | 98.61% | 1.39%
3.8 | 144 | 99.99% | 0.0144% | 10724 | 98.93% | 1.072%
3.9 | 96 | 99.99% | 0.0096% | 8197 | 99.18% | 0.8197%
4 | 63 | 99.99% | 0.0063% | 6209 | 99.38% | 0.6209%
4.1 | 41 | 100% | 0.0041% | 4661 | 99.53% | 0.4661%
4.2 | 26 | 100% | 0.0026% | 3467 | 99.65% | 0.3467%
4.3 | 17 | 100% | 0.0017% | 2555 | 99.74% | 0.2555%
4.4 | 10 | 100% | 0.001% | 1865 | 99.81% | 0.1865%
4.5 | 6 | 100% | 0.0006% | 1349 | 99.87% | 0.1349%
4.6 | 4 | 100% | 0.0004% | 967 | 99.9% | 0.0967%
4.7 | 2 | 100% | 0.0002% | 687 | 99.93% | 0.0687%
4.8 | 1 | 100% | 0.0001% | 483 | 99.95% | 0.0483%
4.9 | 0.96 | 100% | 9.6e-05% | 336 | 99.97% | 0.0336%
5 | 0.574 | 100% | 5.74e-05% | 232 | 99.98% | 0.0232%
5.1 | 0.34 | 100% | 3.4e-05% | 159 | 99.98% | 0.0159%
5.2 | 0.2 | 100% | 2e-05% | 107 | 99.99% | 0.0107%
5.3 | 0.116 | 100% | 1.16e-05% | 72 | 99.99% | 0.0072%
5.4 | 0.067 | 100% | 6.7e-06% | 48 | 100% | 0.0048%
5.5 | 0.038 | 100% | 3.8e-06% | 31 | 100% | 0.0031%
5.6 | 0.021 | 100% | 2.1e-06% | 20 | 100% | 0.002%
5.7 | 0.012 | 100% | 1.2e-06% | 13.35 | 100% | 0.001335%
5.8 | 0.007 | 100% | 7e-07% | 8.55 | 100% | 0.000855%
5.9 | 0.004 | 100% | 4e-07% | 5.42 | 100% | 0.000542%
6 | 0.002 | 100% | 2e-07% | 3.4 | 100% | 0.00034%

## Sample_Size_Calculator
Sample Size Calculator
Continuous | Data Type: | Discrete
Discrete | Enter Proportion Defective: | 0.5
| Acceptable Margin of Error: | 0.05
| Required Sample Size @ 99% CI | 666
| Required Sample Size @ 95% CI | 385
| Required Sample Size @ 90% CI | 271

## Z_Distribution_Table
Table of Probabilities for the Standard Normal (Z) Distribution
Right Tailed Distribution
Z | 0 | 0.01 | 0.02 | 0.03 | 0.04 | 0.05 | 0.06 | 0.07 | 0.08 | 0.09
0 | 0.5 | 0.49601 | 0.49202 | 0.48803 | 0.48405 | 0.48006 | 0.47608 | 0.4721 | 0.46812 | 0.46414
0.1 | 0.46017 | 0.4562 | 0.45224 | 0.44828 | 0.44433 | 0.44038 | 0.43644 | 0.43251 | 0.42858 | 0.42465
0.2 | 0.42074 | 0.41683 | 0.41294 | 0.40905 | 0.40517 | 0.40129 | 0.39743 | 0.39358 | 0.38974 | 0.38591
0.3 | 0.38209 | 0.37828 | 0.37448 | 0.3707 | 0.36693 | 0.36317 | 0.35942 | 0.35569 | 0.35197 | 0.34827
0.4 | 0.34458 | 0.3409 | 0.33724 | 0.3336 | 0.32997 | 0.32636 | 0.32276 | 0.31918 | 0.31561 | 0.31207
0.5 | 0.30854 | 0.30503 | 0.30153 | 0.29806 | 0.2946 | 0.29116 | 0.28774 | 0.28434 | 0.28096 | 0.2776
0.6 | 0.27425 | 0.27093 | 0.26763 | 0.26435 | 0.26109 | 0.25785 | 0.25463 | 0.25143 | 0.24825 | 0.2451
0.7 | 0.24196 | 0.23885 | 0.23576 | 0.2327 | 0.22965 | 0.22663 | 0.22363 | 0.22065 | 0.2177 | 0.21476
0.8 | 0.21186 | 0.20897 | 0.20611 | 0.20327 | 0.20045 | 0.19766 | 0.19489 | 0.19215 | 0.18943 | 0.18673
0.9 | 0.18406 | 0.18141 | 0.17879 | 0.17619 | 0.17361 | 0.17106 | 0.16853 | 0.16602 | 0.16354 | 0.16109
1 | 0.15866 | 0.15625 | 0.15386 | 0.15151 | 0.14917 | 0.14686 | 0.14457 | 0.14231 | 0.14007 | 0.13786
1.1 | 0.13567 | 0.1335 | 0.13136 | 0.12924 | 0.12714 | 0.12507 | 0.12302 | 0.121 | 0.119 | 0.11702
1.2 | 0.11507 | 0.11314 | 0.11123 | 0.10935 | 0.10749 | 0.10565 | 0.10383 | 0.10204 | 0.10027 | 0.098525
1.3 | 0.0968 | 0.095098 | 0.093418 | 0.091759 | 0.090123 | 0.088508 | 0.086915 | 0.085343 | 0.083793 | 0.082264
1.4 | 0.080757 | 0.07927 | 0.077804 | 0.076359 | 0.074934 | 0.073529 | 0.072145 | 0.070781 | 0.069437 | 0.068112
1.5 | 0.066807 | 0.065522 | 0.064255 | 0.063008 | 0.06178 | 0.060571 | 0.05938 | 0.058208 | 0.057053 | 0.055917
1.6 | 0.054799 | 0.053699 | 0.052616 | 0.051551 | 0.050503 | 0.049471 | 0.048457 | 0.04746 | 0.046479 | 0.045514
1.7 | 0.044565 | 0.043633 | 0.042716 | 0.041815 | 0.04093 | 0.040059 | 0.039204 | 0.038364 | 0.037538 | 0.036727
1.8 | 0.03593 | 0.035148 | 0.03438 | 0.033625 | 0.032884 | 0.032157 | 0.031443 | 0.030742 | 0.030054 | 0.029379
1.9 | 0.028717 | 0.028067 | 0.027429 | 0.026803 | 0.02619 | 0.025588 | 0.024998 | 0.024419 | 0.023852 | 0.023295
2 | 0.02275 | 0.022216 | 0.021692 | 0.021178 | 0.020675 | 0.020182 | 0.019699 | 0.019226 | 0.018763 | 0.018309
2.1 | 0.017864 | 0.017429 | 0.017003 | 0.016586 | 0.016177 | 0.015778 | 0.015386 | 0.015003 | 0.014629 | 0.014262
2.2 | 0.013903 | 0.013553 | 0.013209 | 0.012874 | 0.012545 | 0.012224 | 0.011911 | 0.011604 | 0.011304 | 0.011011
2.3 | 0.010724 | 0.010444 | 0.01017 | 0.0099031 | 0.0096419 | 0.0093867 | 0.0091375 | 0.008894 | 0.0086563 | 0.0084242
2.4 | 0.0081975 | 0.0079763 | 0.0077603 | 0.0075494 | 0.0073436 | 0.0071428 | 0.0069469 | 0.0067557 | 0.0065691 | 0.0063872
2.5 | 0.0062097 | 0.0060366 | 0.0058677 | 0.0057031 | 0.0055426 | 0.0053861 | 0.0052336 | 0.0050849 | 0.00494 | 0.0047988
2.6 | 0.0046612 | 0.0045271 | 0.0043965 | 0.0042692 | 0.0041453 | 0.0040246 | 0.003907 | 0.0037926 | 0.0036811 | 0.0035726
2.7 | 0.003467 | 0.0033642 | 0.0032641 | 0.0031667 | 0.003072 | 0.0029798 | 0.0028901 | 0.0028028 | 0.0027179 | 0.0026354
2.8 | 0.0025551 | 0.0024771 | 0.0024012 | 0.0023274 | 0.0022557 | 0.002186 | 0.0021182 | 0.0020524 | 0.0019884 | 0.0019262
2.9 | 0.0018658 | 0.0018071 | 0.0017502 | 0.0016948 | 0.0016411 | 0.0015889 | 0.0015382 | 0.001489 | 0.0014412 | 0.0013949
3 | 0.0013499 | 0.0013062 | 0.0012639 | 0.0012228 | 0.0011829 | 0.0011442 | 0.0011067 | 0.0010703 | 0.001035 | 0.0010008
3.1 | 0.0009676 | 0.00093544 | 0.00090426 | 0.00087403 | 0.00084474 | 0.00081635 | 0.00078885 | 0.00076219 | 0.00073638 | 0.00071136
3.2 | 0.00068714 | 0.00066367 | 0.00064095 | 0.00061895 | 0.00059765 | 0.00057703 | 0.00055706 | 0.00053774 | 0.00051904 | 0.00050094
3.3 | 0.00048342 | 0.00046648 | 0.00045009 | 0.00043423 | 0.00041889 | 0.00040406 | 0.00038971 | 0.00037584 | 0.00036243 | 0.00034946
3.4 | 0.00033693 | 0.00032481 | 0.00031311 | 0.00030179 | 0.00029086 | 0.00028029 | 0.00027009 | 0.00026023 | 0.00025071 | 0.00024151
3.5 | 0.00023263 | 0.00022405 | 0.00021577 | 0.00020778 | 0.00020006 | 0.00019262 | 0.00018543 | 0.00017849 | 0.0001718 | 0.00016534
3.6 | 0.00015911 | 0.0001531 | 0.0001473 | 0.00014171 | 0.00013632 | 0.00013112 | 0.00012611 | 0.00012128 | 0.00011662 | 0.00011213
3.7 | 0.0001078 | 0.00010363 | 9.9611e-05 | 9.574e-05 | 9.201e-05 | 8.8417e-05 | 8.4957e-05 | 8.1624e-05 | 7.8414e-05 | 7.5324e-05
3.8 | 7.2348e-05 | 6.9483e-05 | 6.6726e-05 | 6.4072e-05 | 6.1517e-05 | 5.9059e-05 | 5.6694e-05 | 5.4418e-05 | 5.2228e-05 | 5.0122e-05
3.9 | 4.8096e-05 | 4.6148e-05 | 4.4274e-05 | 4.2473e-05 | 4.0741e-05 | 3.9076e-05 | 3.7475e-05 | 3.5936e-05 | 3.4458e-05 | 3.3037e-05
4 | 3.1671e-05 | 3.0359e-05 | 2.9099e-05 | 2.7888e-05 | 2.6726e-05 | 2.5609e-05 | 2.4536e-05 | 2.3507e-05 | 2.2518e-05 | 2.1569e-05
4.1 | 2.0658e-05 | 1.9783e-05 | 1.8944e-05 | 1.8138e-05 | 1.7365e-05 | 1.6624e-05 | 1.5912e-05 | 1.523e-05 | 1.4575e-05 | 1.3948e-05
4.2 | 1.3346e-05 | 1.2769e-05 | 1.2215e-05 | 1.1685e-05 | 1.1176e-05 | 1.0689e-05 | 1.0221e-05 | 9.7736e-06 | 9.3447e-06 | 8.9337e-06
4.3 | 8.5399e-06 | 8.1627e-06 | 7.8015e-06 | 7.4555e-06 | 7.1241e-06 | 6.8069e-06 | 6.5031e-06 | 6.2123e-06 | 5.934e-06 | 5.6675e-06
4.4 | 5.4125e-06 | 5.1685e-06 | 4.935e-06 | 4.7117e-06 | 4.4979e-06 | 4.2935e-06 | 4.098e-06 | 3.911e-06 | 3.7322e-06 | 3.5612e-06
4.5 | 3.3977e-06 | 3.2414e-06 | 3.092e-06 | 2.9492e-06 | 2.8127e-06 | 2.6823e-06 | 2.5577e-06 | 2.4386e-06 | 2.3249e-06 | 2.2162e-06
4.6 | 2.1125e-06 | 2.0133e-06 | 1.9187e-06 | 1.8283e-06 | 1.742e-06 | 1.6597e-06 | 1.581e-06 | 1.506e-06 | 1.4344e-06 | 1.366e-06
4.7 | 1.3008e-06 | 1.2386e-06 | 1.1792e-06 | 1.1226e-06 | 1.0686e-06 | 1.0171e-06 | 9.6796e-07 | 9.2113e-07 | 8.7648e-07 | 8.3391e-07
4.8 | 7.9333e-07 | 7.5465e-07 | 7.1779e-07 | 6.8267e-07 | 6.492e-07 | 6.1731e-07 | 5.8693e-07 | 5.5799e-07 | 5.3043e-07 | 5.0418e-07
4.9 | 4.7918e-07 | 4.5538e-07 | 4.3272e-07 | 4.1115e-07 | 3.9061e-07 | 3.7107e-07 | 3.5247e-07 | 3.3476e-07 | 3.1792e-07 | 3.019e-07
Standard Normal (Z) Distribution:

## t_Distribution_Table
Table of Probabilities for Student's t-Distribution
df | 0.6 | 0.7 | 0.8 | 0.9 | 0.95 | 0.975 | 0.99 | 0.995
1 | 0.325 | 0.727 | 1.376 | 3.078 | 6.314 | 12.706 | 31.821 | 63.657
2 | 0.289 | 0.617 | 1.061 | 1.886 | 2.92 | 4.303 | 6.965 | 9.925
3 | 0.27667 | 0.58439 | 0.97847 | 1.6377 | 2.3534 | 3.1824 | 4.5407 | 5.8409
4 | 0.27072 | 0.56865 | 0.94096 | 1.5332 | 2.1319 | 2.7765 | 3.747 | 4.6041
5 | 0.26718 | 0.55943 | 0.91954 | 1.4759 | 2.0151 | 2.5706 | 3.3649 | 4.0321
6 | 0.26483 | 0.55338 | 0.9057 | 1.4398 | 1.9432 | 2.4469 | 3.1427 | 3.7074
7 | 0.26317 | 0.54911 | 0.89603 | 1.4149 | 1.8946 | 2.3646 | 2.9979 | 3.4995
8 | 0.26192 | 0.54593 | 0.88889 | 1.3968 | 1.8596 | 2.306 | 2.8965 | 3.3554
9 | 0.26096 | 0.54348 | 0.8834 | 1.383 | 1.8331 | 2.2622 | 2.8214 | 3.2498
10 | 0.26018 | 0.54153 | 0.87906 | 1.3722 | 1.8125 | 2.2281 | 2.7638 | 3.1693
11 | 0.25956 | 0.53994 | 0.87553 | 1.3634 | 1.7959 | 2.201 | 2.7181 | 3.1058
12 | 0.25903 | 0.53862 | 0.87261 | 1.3562 | 1.7823 | 2.1788 | 2.681 | 3.0545
13 | 0.25859 | 0.5375 | 0.87015 | 1.3502 | 1.7709 | 2.1604 | 2.6503 | 3.0123
14 | 0.25821 | 0.53655 | 0.86805 | 1.345 | 1.7613 | 2.1448 | 2.6245 | 2.9768
15 | 0.25789 | 0.53573 | 0.86624 | 1.3406 | 1.753 | 2.1315 | 2.6025 | 2.9467
16 | 0.2576 | 0.53501 | 0.86467 | 1.3368 | 1.7459 | 2.1199 | 2.5835 | 2.9208
17 | 0.25735 | 0.53438 | 0.86328 | 1.3334 | 1.7396 | 2.1098 | 2.5669 | 2.8982
18 | 0.25712 | 0.53382 | 0.86205 | 1.3304 | 1.7341 | 2.1009 | 2.5524 | 2.8784
19 | 0.25692 | 0.53331 | 0.86095 | 1.3277 | 1.7291 | 2.093 | 2.5395 | 2.8609
20 | 0.25674 | 0.53286 | 0.85996 | 1.3253 | 1.7247 | 2.086 | 2.528 | 2.8453
21 | 0.25658 | 0.53246 | 0.85907 | 1.3232 | 1.7207 | 2.0796 | 2.5177 | 2.8314
22 | 0.25643 | 0.53208 | 0.85827 | 1.3212 | 1.7171 | 2.0739 | 2.5083 | 2.8188
23 | 0.2563 | 0.53175 | 0.85753 | 1.3195 | 1.7139 | 2.0687 | 2.4999 | 2.8073
24 | 0.25617 | 0.53144 | 0.85686 | 1.3178 | 1.7109 | 2.0639 | 2.4922 | 2.7969
25 | 0.25606 | 0.53115 | 0.85624 | 1.3163 | 1.7081 | 2.0595 | 2.4851 | 2.7874
26 | 0.25595 | 0.53089 | 0.85567 | 1.315 | 1.7056 | 2.0555 | 2.4786 | 2.7787
27 | 0.25586 | 0.53065 | 0.85514 | 1.3137 | 1.7033 | 2.0518 | 2.4727 | 2.7707
28 | 0.25577 | 0.53042 | 0.85465 | 1.3125 | 1.7011 | 2.0484 | 2.4671 | 2.7633
29 | 0.25568 | 0.53021 | 0.85419 | 1.3114 | 1.6991 | 2.0452 | 2.462 | 2.7564
30 | 0.25561 | 0.53002 | 0.85377 | 1.3104 | 1.6973 | 2.0423 | 2.4573 | 2.75
40 | 0.25504 | 0.52861 | 0.8507 | 1.3031 | 1.6839 | 2.0211 | 2.4233 | 2.7045
60 | 0.25447 | 0.5272 | 0.84765 | 1.2958 | 1.6706 | 2.0003 | 2.3901 | 2.6603
120 | 0.25391 | 0.5258 | 0.84463 | 1.2887 | 1.6577 | 1.9799 | 2.3578 | 2.6174
df (degrees of freedom) = number of samples - 1
1 - alpha (for one tail) or 1 - alpha/2 (for two tails)

## F_Distribution_Table
Table of Probabilities for the F Distribution
| Alpha = | 0.05
D/N | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 20 | 24 | 30 | 40 | 60 | 120
1 | 161.4476 | 199.5 | 215.7073 | 224.5832 | 230.1619 | 233.986 | 236.7684 | 238.8827 | 240.5433 | 241.8817 | 242.9835 | 243.906 | 244.6898 | 245.364 | 245.9499 | 248.0131 | 249.0518 | 250.0951 | 251.1432 | 252.1957 | 253.2529
2 | 18.5128 | 19 | 19.1643 | 19.2468 | 19.2964 | 19.3295 | 19.3532 | 19.371 | 19.3848 | 19.3959 | 19.405 | 19.4125 | 19.4189 | 19.4244 | 19.4291 | 19.4458 | 19.4541 | 19.4624 | 19.4707 | 19.4791 | 19.4874
3 | 10.128 | 9.5521 | 9.2766 | 9.1172 | 9.0135 | 8.9406 | 8.8867 | 8.8452 | 8.8123 | 8.7855 | 8.7633 | 8.7446 | 8.7287 | 8.7149 | 8.7029 | 8.6602 | 8.6385 | 8.6166 | 8.5944 | 8.572 | 8.5494
4 | 7.7086 | 6.9443 | 6.5914 | 6.3882 | 6.2561 | 6.1631 | 6.0942 | 6.041 | 5.9988 | 5.9644 | 5.9358 | 5.9117 | 5.8911 | 5.8733 | 5.8578 | 5.8025 | 5.7744 | 5.7459 | 5.717 | 5.6877 | 5.6581
5 | 6.6079 | 5.7861 | 5.4095 | 5.1922 | 5.0503 | 4.9503 | 4.8759 | 4.8183 | 4.7725 | 4.7351 | 4.704 | 4.6777 | 4.6552 | 4.6358 | 4.6188 | 4.5581 | 4.5272 | 4.4957 | 4.4638 | 4.4314 | 4.3985
6 | 5.9874 | 5.1433 | 4.7571 | 4.5337 | 4.3874 | 4.2839 | 4.2067 | 4.1468 | 4.099 | 4.06 | 4.0274 | 3.9999 | 3.9764 | 3.9559 | 3.9381 | 3.8742 | 3.8415 | 3.8082 | 3.7743 | 3.7398 | 3.7047
7 | 5.5914 | 4.7374 | 4.3468 | 4.1203 | 3.9715 | 3.866 | 3.787 | 3.7257 | 3.6767 | 3.6365 | 3.603 | 3.5747 | 3.5503 | 3.5292 | 3.5107 | 3.4445 | 3.4105 | 3.3758 | 3.3404 | 3.3043 | 3.2674
8 | 5.3177 | 4.459 | 4.0662 | 3.8379 | 3.6875 | 3.5806 | 3.5005 | 3.4381 | 3.3881 | 3.3472 | 3.313 | 3.2839 | 3.259 | 3.2374 | 3.2184 | 3.1503 | 3.1152 | 3.0794 | 3.0428 | 3.0053 | 2.9669
9 | 5.1174 | 4.2565 | 3.8625 | 3.6331 | 3.4817 | 3.3738 | 3.2927 | 3.2296 | 3.1789 | 3.1373 | 3.1025 | 3.0729 | 3.0475 | 3.0255 | 3.0061 | 2.9365 | 2.9005 | 2.8637 | 2.8259 | 2.7872 | 2.7475
10 | 4.9646 | 4.1028 | 3.7083 | 3.478 | 3.3258 | 3.2172 | 3.1355 | 3.0717 | 3.0204 | 2.9782 | 2.943 | 2.913 | 2.8872 | 2.8647 | 2.845 | 2.774 | 2.7372 | 2.6996 | 2.6609 | 2.6211 | 2.5801
11 | 4.8443 | 3.9823 | 3.5874 | 3.3567 | 3.2039 | 3.0946 | 3.0123 | 2.948 | 2.8962 | 2.8536 | 2.8179 | 2.7876 | 2.7614 | 2.7386 | 2.7186 | 2.6464 | 2.609 | 2.5705 | 2.5309 | 2.4901 | 2.448
12 | 4.7472 | 3.8853 | 3.4903 | 3.2592 | 3.1059 | 2.9961 | 2.9134 | 2.8486 | 2.7964 | 2.7534 | 2.7173 | 2.6866 | 2.6602 | 2.6371 | 2.6169 | 2.5436 | 2.5055 | 2.4663 | 2.4259 | 2.3842 | 2.341
13 | 4.6672 | 3.8056 | 3.4105 | 3.1791 | 3.0254 | 2.9153 | 2.8321 | 2.7669 | 2.7144 | 2.671 | 2.6347 | 2.6037 | 2.5769 | 2.5536 | 2.5331 | 2.4589 | 2.4202 | 2.3803 | 2.3392 | 2.2966 | 2.2524
14 | 4.6001 | 3.7389 | 3.3439 | 3.1122 | 2.9582 | 2.8477 | 2.7642 | 2.6987 | 2.6458 | 2.6022 | 2.5655 | 2.5342 | 2.5073 | 2.4837 | 2.463 | 2.3879 | 2.3487 | 2.3082 | 2.2664 | 2.2229 | 2.1778
15 | 4.5431 | 3.6823 | 3.2874 | 3.0556 | 2.9013 | 2.7905 | 2.7066 | 2.6408 | 2.5876 | 2.5437 | 2.5068 | 2.4753 | 2.4481 | 2.4244 | 2.4034 | 2.3275 | 2.2878 | 2.2468 | 2.2043 | 2.1601 | 2.1141
16 | 4.494 | 3.6337 | 3.2389 | 3.0069 | 2.8524 | 2.7413 | 2.6572 | 2.5911 | 2.5377 | 2.4935 | 2.4564 | 2.4247 | 2.3973 | 2.3733 | 2.3522 | 2.2756 | 2.2354 | 2.1938 | 2.1507 | 2.1058 | 2.0589
17 | 4.4513 | 3.5915 | 3.1968 | 2.9647 | 2.81 | 2.6987 | 2.6143 | 2.548 | 2.4943 | 2.4499 | 2.4126 | 2.3807 | 2.3531 | 2.329 | 2.3077 | 2.2304 | 2.1898 | 2.1477 | 2.104 | 2.0584 | 2.0107
18 | 4.4139 | 3.5546 | 3.1599 | 2.9277 | 2.7729 | 2.6613 | 2.5767 | 2.5102 | 2.4563 | 2.4117 | 2.3742 | 2.3421 | 2.3143 | 2.29 | 2.2686 | 2.1906 | 2.1497 | 2.1071 | 2.0629 | 2.0166 | 1.9681
19 | 4.3807 | 3.5219 | 3.1274 | 2.8951 | 2.7401 | 2.6283 | 2.5435 | 2.4768 | 2.4227 | 2.3779 | 2.3402 | 2.308 | 2.28 | 2.2556 | 2.2341 | 2.1555 | 2.1141 | 2.0712 | 2.0264 | 1.9795 | 1.9302
20 | 4.3512 | 3.4928 | 3.0984 | 2.8661 | 2.7109 | 2.599 | 2.514 | 2.4471 | 2.3928 | 2.3479 | 2.31 | 2.2776 | 2.2495 | 2.225 | 2.2033 | 2.1242 | 2.0825 | 2.0391 | 1.9938 | 1.9464 | 1.8963
21 | 4.3248 | 3.4668 | 3.0725 | 2.8401 | 2.6848 | 2.5727 | 2.4876 | 2.4205 | 2.366 | 2.321 | 2.2829 | 2.2504 | 2.2222 | 2.1975 | 2.1757 | 2.096 | 2.054 | 2.0102 | 1.9645 | 1.9165 | 1.8657
22 | 4.3009 | 3.4434 | 3.0491 | 2.8167 | 2.6613 | 2.5491 | 2.4638 | 2.3965 | 2.3419 | 2.2967 | 2.2585 | 2.2258 | 2.1975 | 2.1727 | 2.1508 | 2.0707 | 2.0283 | 1.9842 | 1.938 | 1.8894 | 1.838
23 | 4.2793 | 3.4221 | 3.028 | 2.7955 | 2.64 | 2.5277 | 2.4422 | 2.3748 | 2.3201 | 2.2747 | 2.2364 | 2.2036 | 2.1752 | 2.1502 | 2.1282 | 2.0476 | 2.005 | 1.9605 | 1.9139 | 1.8648 | 1.8128
24 | 4.2597 | 3.4028 | 3.0088 | 2.7763 | 2.6207 | 2.5082 | 2.4226 | 2.3551 | 2.3002 | 2.2547 | 2.2163 | 2.1834 | 2.1548 | 2.1298 | 2.1077 | 2.0267 | 1.9838 | 1.939 | 1.892 | 1.8424 | 1.7896
25 | 4.2417 | 3.3852 | 2.9912 | 2.7587 | 2.603 | 2.4904 | 2.4047 | 2.3371 | 2.2821 | 2.2365 | 2.1979 | 2.1649 | 2.1362 | 2.1111 | 2.0889 | 2.0075 | 1.9643 | 1.9192 | 1.8718 | 1.8217 | 1.7684
26 | 4.2252 | 3.369 | 2.9752 | 2.7426 | 2.5868 | 2.4741 | 2.3883 | 2.3205 | 2.2655 | 2.2197 | 2.1811 | 2.1479 | 2.1192 | 2.0939 | 2.0716 | 1.9898 | 1.9464 | 1.901 | 1.8533 | 1.8027 | 1.7488
27 | 4.21 | 3.3541 | 2.9604 | 2.7278 | 2.5719 | 2.4591 | 2.3732 | 2.3053 | 2.2501 | 2.2043 | 2.1655 | 2.1323 | 2.1035 | 2.0781 | 2.0558 | 1.9736 | 1.9299 | 1.8842 | 1.8361 | 1.7851 | 1.7306
28 | 4.196 | 3.3404 | 2.9467 | 2.7141 | 2.5581 | 2.4453 | 2.3593 | 2.2913 | 2.236 | 2.19 | 2.1512 | 2.1179 | 2.0889 | 2.0635 | 2.0411 | 1.9586 | 1.9147 | 1.8687 | 1.8203 | 1.7689 | 1.7138
29 | 4.183 | 3.3277 | 2.934 | 2.7014 | 2.5454 | 2.4324 | 2.3463 | 2.2783 | 2.2229 | 2.1768 | 2.1379 | 2.1045 | 2.0755 | 2.05 | 2.0275 | 1.9446 | 1.9005 | 1.8543 | 1.8055 | 1.7537 | 1.6981
30 | 4.1709 | 3.3158 | 2.9223 | 2.6896 | 2.5336 | 2.4205 | 2.3343 | 2.2662 | 2.2107 | 2.1646 | 2.1256 | 2.0921 | 2.063 | 2.0374 | 2.0148 | 1.9317 | 1.8874 | 1.8409 | 1.7918 | 1.7396 | 1.6835
40 | 4.0847 | 3.2317 | 2.8387 | 2.606 | 2.4495 | 2.3359 | 2.249 | 2.1802 | 2.124 | 2.0772 | 2.0376 | 2.0035 | 1.9738 | 1.9476 | 1.9245 | 1.8389 | 1.7929 | 1.7444 | 1.6928 | 1.6373 | 1.5766
60 | 4.0012 | 3.1504 | 2.7581 | 2.5252 | 2.3683 | 2.2541 | 2.1665 | 2.097 | 2.0401 | 1.9926 | 1.9522 | 1.9174 | 1.887 | 1.8602 | 1.8364 | 1.748 | 1.7001 | 1.6491 | 1.5943 | 1.5343 | 1.4673
120 | 3.9201 | 3.0718 | 2.6802 | 2.4472 | 2.2899 | 2.175 | 2.0868 | 2.0164 | 1.9588 | 1.9105 | 1.8693 | 1.8337 | 1.8026 | 1.775 | 1.7505 | 1.6587 | 1.6084 | 1.5543 | 1.4952 | 1.429 | 1.3519
Right Tailed, D/N = df in denominator = down the rows, df in numerator = across the columns | [20 empty] | Note: Table is for an alpha of 0.05
Table of Probabilities for F Distribution

## Chi_Square_Distribution_Table
Table of Probabilities for the Chi-Squared Distribution
Alpha Risk
df | 0.995 | 0.99 | 0.975 | 0.95 | 0.9 | 0.75 | 0.5 | 0.25 | 0.1 | 0.05 | 0.25 | 0.01 | 0.005 | 0.001
1 | 3.927e-05 | 0.00015709 | 0.00098207 | 0.0039321 | 0.015791 | 0.10153 | 0.45494 | 1.3233 | 2.7055 | 3.8415 | 1.3233 | 6.6349 | 7.8794 | 10.8276
2 | 0.010025 | 0.020101 | 0.050636 | 0.10259 | 0.21072 | 0.57536 | 1.3863 | 2.7726 | 4.6052 | 5.9915 | 2.7726 | 9.2103 | 10.5966 | 13.8155
3 | 0.071722 | 0.11483 | 0.2158 | 0.35185 | 0.58437 | 1.2125 | 2.366 | 4.1083 | 6.2514 | 7.8147 | 4.1083 | 11.3449 | 12.8382 | 16.2662
4 | 0.20699 | 0.29711 | 0.48442 | 0.71072 | 1.0636 | 1.9226 | 3.3567 | 5.3853 | 7.7794 | 9.4877 | 5.3853 | 13.2767 | 14.8603 | 18.4668
5 | 0.41174 | 0.5543 | 0.83121 | 1.1455 | 1.6103 | 2.6746 | 4.3515 | 6.6257 | 9.2364 | 11.0705 | 6.6257 | 15.0863 | 16.7496 | 20.515
6 | 0.67573 | 0.87209 | 1.2373 | 1.6354 | 2.2041 | 3.4546 | 5.3481 | 7.8408 | 10.6446 | 12.5916 | 7.8408 | 16.8119 | 18.5476 | 22.4577
7 | 0.98926 | 1.239 | 1.6899 | 2.1673 | 2.8331 | 4.2549 | 6.3458 | 9.0371 | 12.017 | 14.0671 | 9.0371 | 18.4753 | 20.2777 | 24.3219
8 | 1.3444 | 1.6465 | 2.1797 | 2.7326 | 3.4895 | 5.0706 | 7.3441 | 10.2189 | 13.3616 | 15.5073 | 10.2189 | 20.0902 | 21.955 | 26.1245
9 | 1.7349 | 2.0879 | 2.7004 | 3.3251 | 4.1682 | 5.8988 | 8.3428 | 11.3888 | 14.6837 | 16.919 | 11.3888 | 21.666 | 23.5894 | 27.8772
10 | 2.1559 | 2.5582 | 3.247 | 3.9403 | 4.8652 | 6.7372 | 9.3418 | 12.5489 | 15.9872 | 18.307 | 12.5489 | 23.2093 | 25.1882 | 29.5883
11 | 2.6032 | 3.0535 | 3.8157 | 4.5748 | 5.5778 | 7.5841 | 10.341 | 13.7007 | 17.275 | 19.6751 | 13.7007 | 24.725 | 26.7568 | 31.2641
12 | 3.0738 | 3.5706 | 4.4038 | 5.226 | 6.3038 | 8.4384 | 11.3403 | 14.8454 | 18.5493 | 21.0261 | 14.8454 | 26.217 | 28.2995 | 32.9095
13 | 3.565 | 4.1069 | 5.0088 | 5.8919 | 7.0415 | 9.2991 | 12.3398 | 15.9839 | 19.8119 | 22.362 | 15.9839 | 27.6882 | 29.8195 | 34.5282
14 | 4.0747 | 4.6604 | 5.6287 | 6.5706 | 7.7895 | 10.1653 | 13.3393 | 17.1169 | 21.0641 | 23.6848 | 17.1169 | 29.1412 | 31.3193 | 36.1233
15 | 4.6009 | 5.2293 | 6.2621 | 7.2609 | 8.5468 | 11.0365 | 14.3389 | 18.2451 | 22.3071 | 24.9958 | 18.2451 | 30.5779 | 32.8013 | 37.6973
16 | 5.1422 | 5.8122 | 6.9077 | 7.9616 | 9.3122 | 11.9122 | 15.3385 | 19.3689 | 23.5418 | 26.2962 | 19.3689 | 31.9999 | 34.2672 | 39.2524
17 | 5.6972 | 6.4078 | 7.5642 | 8.6718 | 10.0852 | 12.7919 | 16.3382 | 20.4887 | 24.769 | 27.5871 | 20.4887 | 33.4087 | 35.7185 | 40.7902
18 | 6.2648 | 7.0149 | 8.2307 | 9.3905 | 10.8649 | 13.6753 | 17.3379 | 21.6049 | 25.9894 | 28.8693 | 21.6049 | 34.8053 | 37.1565 | 42.3124
19 | 6.844 | 7.6327 | 8.9065 | 10.117 | 11.6509 | 14.562 | 18.3377 | 22.7178 | 27.2036 | 30.1435 | 22.7178 | 36.1909 | 38.5823 | 43.8202
20 | 7.4338 | 8.2604 | 9.5908 | 10.8508 | 12.4426 | 15.4518 | 19.3374 | 23.8277 | 28.412 | 31.4104 | 23.8277 | 37.5662 | 39.9968 | 45.3147
21 | 8.0337 | 8.8972 | 10.2829 | 11.5913 | 13.2396 | 16.3444 | 20.3372 | 24.9348 | 29.6151 | 32.6706 | 24.9348 | 38.9322 | 41.4011 | 46.797
22 | 8.6427 | 9.5425 | 10.9823 | 12.338 | 14.0415 | 17.2396 | 21.337 | 26.0393 | 30.8133 | 33.9244 | 26.0393 | 40.2894 | 42.7957 | 48.2679
23 | 9.2604 | 10.1957 | 11.6886 | 13.0905 | 14.848 | 18.1373 | 22.3369 | 27.1413 | 32.0069 | 35.1725 | 27.1413 | 41.6384 | 44.1813 | 49.7282
24 | 9.8862 | 10.8564 | 12.4012 | 13.8484 | 15.6587 | 19.0373 | 23.3367 | 28.2412 | 33.1962 | 36.415 | 28.2412 | 42.9798 | 45.5585 | 51.1786
25 | 10.5197 | 11.524 | 13.1197 | 14.6114 | 16.4734 | 19.9393 | 24.3366 | 29.3389 | 34.3816 | 37.6525 | 29.3389 | 44.3141 | 46.9279 | 52.6197
26 | 11.1602 | 12.1981 | 13.8439 | 15.3792 | 17.2919 | 20.8434 | 25.3365 | 30.4346 | 35.5632 | 38.8851 | 30.4346 | 45.6417 | 48.2899 | 54.052
27 | 11.8076 | 12.8785 | 14.5734 | 16.1514 | 18.1139 | 21.7494 | 26.3363 | 31.5284 | 36.7412 | 40.1133 | 31.5284 | 46.9629 | 49.6449 | 55.476
28 | 12.4613 | 13.5647 | 15.3079 | 16.9279 | 18.9392 | 22.6572 | 27.3362 | 32.6205 | 37.9159 | 41.3371 | 32.6205 | 48.2782 | 50.9934 | 56.8923
29 | 13.1211 | 14.2565 | 16.0471 | 17.7084 | 19.7677 | 23.5666 | 28.3361 | 33.7109 | 39.0875 | 42.557 | 33.7109 | 49.5879 | 52.3356 | 58.3012
30 | 13.7867 | 14.9535 | 16.7908 | 18.4927 | 20.5992 | 24.4776 | 29.336 | 34.7997 | 40.256 | 43.773 | 34.7997 | 50.8922 | 53.672 | 59.7031
40 | 20.7065 | 22.1643 | 24.433 | 26.5093 | 29.0505 | 33.6603 | 39.3353 | 45.616 | 51.8051 | 55.7585 | 45.616 | 63.6907 | 66.766 | 73.402
50 | 27.9907 | 29.7067 | 32.3574 | 34.7643 | 37.6886 | 42.9421 | 49.3349 | 56.3336 | 63.1671 | 67.5048 | 56.3336 | 76.1539 | 79.49 | 86.6608
60 | 35.5345 | 37.4849 | 40.4817 | 43.188 | 46.4589 | 52.2938 | 59.3347 | 66.9815 | 74.397 | 79.0819 | 66.9815 | 88.3794 | 91.9517 | 99.6072
70 | 43.2752 | 45.4417 | 48.7576 | 51.7393 | 55.3289 | 61.6983 | 69.3345 | 77.5767 | 85.527 | 90.5312 | 77.5767 | 100.4252 | 104.2149 | 112.3169
80 | 51.1719 | 53.5401 | 57.1532 | 60.3915 | 64.2778 | 71.1445 | 79.3343 | 88.1303 | 96.5782 | 101.8795 | 88.1303 | 112.3288 | 116.3211 | 124.8392
90 | 59.1963 | 61.7541 | 65.6466 | 69.126 | 73.2911 | 80.6247 | 89.3342 | 98.6499 | 107.565 | 113.1453 | 98.6499 | 124.1163 | 128.2989 | 137.2084
100 | 67.3276 | 70.0649 | 74.2219 | 77.9295 | 82.3581 | 90.1332 | 99.3341 | 109.1412 | 118.498 | 124.3421 | 109.1412 | 135.8067 | 140.1695 | 149.4493
Right Tailed Distribution, df = degrees of freedom = (#Rows - 1) x (#Columns - 1)
Chi Square Table of Probabilities: